## Sheet1
Task | Duration | Dependencies
Plan Event | 2
Book Venue | 3 | Plan Event
Arrange Catering | 4 | Plan Event
Send Invitations | 1 | Book Venue
Set Up Venue | 2 | Book Venue, Arrange Catering
Host Event | 1 | Set Up Venue, Send Invitations